## Master Resource Plan
Flight | Step_1_Unload_Machine | Step_1_Unload_Planned_Start | Step_2_Transport_Machine | Step_2_Transport_Planned_Start | Step_3_Infeed_Machine | Step_3_Infeed_Planned_Start
AC832 | Unload Gate 1 | 4/5/2026 15:35 | Transport Cart 1 | 4/5/2026 07:46 | Infeed Station 1 | 4/5/2026 10:56
ET750 | Unload Gate 2 | 4/5/2026 09:13 | Transport Cart 1 | 4/5/2026 12:24 | Infeed Station 1 | 4/5/2026 12:14
FH8116 | Unload Gate 4 | 4/5/2026 15:35 | Transport Cart 1 | 4/5/2026 06:01 | Infeed Station 3 | 4/5/2026 11:43
LH1004 | Unload Gate 1 | 4/5/2026 12:23 | Transport Cart 3 | 4/5/2026 15:35 | Infeed Station 2 | 4/5/2026 11:50
SN1122 | Unload Gate 4 | 4/5/2026 10:01 | Transport Cart 1 | 4/5/2026 09:51 | Infeed Station 1 | 4/5/2026 09:37
SN1124 | Unload Gate 1 | 4/5/2026 13:07 | Transport Cart 1 | 4/5/2026 15:33 | Infeed Station 3 | 4/5/2026 07:56
SN206 | Unload Gate 3 | 4/5/2026 12:56 | Transport Cart 2 | 4/5/2026 13:06 | Infeed Station 1 | 4/5/2026 07:07
SN229 | Unload Gate 2 | 4/5/2026 13:13 | Transport Cart 2 | 4/5/2026 09:33 | Infeed Station 3 | 4/5/2026 10:37
SN278 | Unload Gate 2 | 4/5/2026 15:34 | Transport Cart 1 | 4/5/2026 10:04 | Infeed Station 2 | 4/5/2026 11:24
SN2900 | Unload Gate 4 | 4/5/2026 15:22 | Transport Cart 2 | 4/5/2026 15:24 | Infeed Station 2 | 4/5/2026 08:42
SN3326 | Unload Gate 4 | 4/5/2026 14:22 | Transport Cart 1 | 4/5/2026 13:01 | Infeed Station 3 | 4/5/2026 11:43
SN358 | Unload Gate 1 | 4/5/2026 12:11 | Transport Cart 3 | 4/5/2026 10:28 | Infeed Station 1 | 4/5/2026 11:55
SN379 | Unload Gate 3 | 4/5/2026 10:44 | Transport Cart 3 | 4/5/2026 12:01 | Infeed Station 3 | 4/5/2026 10:43
SN3800 | Unload Gate 1 | 4/5/2026 13:39 | Transport Cart 3 | 4/5/2026 06:39 | Infeed Station 1 | 4/5/2026 06:24
TB1552 | Unload Gate 3 | 4/5/2026 08:51 | Transport Cart 2 | 4/5/2026 12:45 | Infeed Station 2 | 4/5/2026 07:51
TB2632 | Unload Gate 3 | 4/5/2026 13:37 | Transport Cart 1 | 4/5/2026 15:35 | Infeed Station 1 | 4/5/2026 09:47
TB2662 | Unload Gate 1 | 4/5/2026 10:26 | Transport Cart 1 | 4/5/2026 12:39 | Infeed Station 1 | 4/5/2026 09:39
TG934 | Unload Gate 4 | 4/5/2026 12:50 | Transport Cart 1 | 4/5/2026 10:15 | Infeed Station 2 | 4/5/2026 10:24
UA950 | Unload Gate 4 | 4/5/2026 08:45 | Transport Cart 2 | 4/5/2026 15:35 | Infeed Station 2 | 4/5/2026 10:53
UA994 | Unload Gate 3 | 4/5/2026 15:35 | Transport Cart 2 | 4/5/2026 08:43 | Infeed Station 3 | 4/5/2026 12:07
XR5402 | Unload Gate 2 | 4/5/2026 10:18 | Transport Cart 1 | 4/5/2026 11:29 | Infeed Station 1 | 4/5/2026 09:31

## KPI Analysis
TSSP SYSTEM KPIs (Averages over Scenarios) | VALUE
Number of Scenarios Evaluated | 10
Expected Total Operation Makespan | 436.00 min
Expected Average Handling Time | 45.35 min
Expected Maximum Handling Time | 88.90 min
Overall Maximum Handling Time | 119.00 min
Expected Maximum Idle Time Observed | 27.00 min
Expected Maximum Slack Consumption (S1/S2/S3) | 10.00/7.00/10.00 min
SOLVER TECHNICALS
Variables / Constraints | 1027504 / 62787
Gurobi Solve Time | 74.1210 sec
Optimality Gap | 1.8670 %
PARAMETER VALUES
Gate Capacity | 4
Transport Capacity | 3
Infeed Capacity | 3
Slack Unload | 10
Slack Transport | 7
Slack Infeed | 10
Time Buffer (B) | 30
SCENARIO PERFORMANCE BREAKDOWN
Scenario ID | Avg Handling ¦ Max Handling
Scenario 1 | 46.19 min ¦ 87.00 min
Scenario 2 | 44.38 min ¦ 86.00 min
Scenario 3 | 50.48 min ¦ 92.00 min
Scenario 4 | 46.52 min ¦ 82.00 min
Scenario 5 | 46.19 min ¦ 78.00 min
Scenario 6 | 44.33 min ¦ 84.00 min
Scenario 7 | 40.95 min ¦ 86.00 min
Scenario 8 | 48.29 min ¦ 89.00 min
Scenario 9 | 43.00 min ¦ 119.00 min
Scenario 10 | 43.14 min ¦ 86.00 min
Resource | Expected Utilization %
Unload Gate 1 | 13.95
Unload Gate 2 | 9.3
Unload Gate 3 | 11.63
Unload Gate 4 | 13.95
Transport Cart 1 | 5.01
Transport Cart 2 | 2.73
Transport Cart 3 | 1.82
Infeed Station 1 | 37.75
Infeed Station 2 | 25.16
Infeed Station 3 | 25.16

## Scenario Realizations
Scenario_ID | Flight | Arrival | Start_Unloading | End_Unloading | Idle_Unloading | Start_Transport | End_Transport | Idle_Transport | Start_Infeed | End_Infeed | Idle_Infeed | Total_Handling_Time | Total_Idle
1 | AC832 | 4/5/2026 10:43 | 4/5/2026 10:43 | 4/5/2026 10:57 | 0 | 4/5/2026 10:57 | 4/5/2026 10:59 | 0 | 4/5/2026 10:59 | 4/5/2026 11:33 | 0 | 50 | 0
1 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:10 | 0 | 4/5/2026 12:10 | 4/5/2026 12:12 | 0 | 4/5/2026 12:15 | 4/5/2026 13:01 | 3 | 87 | 3
1 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:48 | 4/5/2026 13:00 | 0 | 4/5/2026 13:00 | 4/5/2026 13:03 | 0 | 4/5/2026 13:03 | 4/5/2026 13:10 | 0 | 22 | 0
1 | LH1004 | 4/5/2026 09:53 | 4/5/2026 10:03 | 4/5/2026 10:06 | 10 | 4/5/2026 10:13 | 4/5/2026 10:15 | 7 | 4/5/2026 10:25 | 4/5/2026 10:32 | 10 | 39 | 27
1 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:23 | 4/5/2026 09:27 | 4 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 24
1 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:28 | 4/5/2026 07:39 | 9 | 4/5/2026 07:44 | 4/5/2026 07:46 | 5 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 24
1 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:49 | 4/5/2026 06:58 | 1 | 4/5/2026 07:03 | 4/5/2026 07:05 | 5 | 4/5/2026 07:07 | 4/5/2026 07:30 | 2 | 42 | 8
1 | SN229 | 4/5/2026 10:26 | 4/5/2026 10:26 | 4/5/2026 10:34 | 0 | 4/5/2026 10:34 | 4/5/2026 10:37 | 0 | 4/5/2026 10:37 | 4/5/2026 11:06 | 0 | 40 | 0
1 | SN278 | 4/5/2026 10:42 | 4/5/2026 10:52 | 4/5/2026 11:05 | 10 | 4/5/2026 11:12 | 4/5/2026 11:14 | 7 | 4/5/2026 11:24 | 4/5/2026 11:36 | 10 | 54 | 27
1 | SN2900 | 4/5/2026 08:33 | 4/5/2026 08:33 | 4/5/2026 08:39 | 0 | 4/5/2026 08:41 | 4/5/2026 08:42 | 2 | 4/5/2026 08:42 | 4/5/2026 08:46 | 0 | 13 | 2
1 | SN3326 | 4/5/2026 08:05 | 4/5/2026 08:15 | 4/5/2026 08:23 | 10 | 4/5/2026 08:30 | 4/5/2026 08:31 | 7 | 4/5/2026 08:41 | 4/5/2026 09:01 | 10 | 56 | 27
1 | SN358 | 4/5/2026 11:13 | 4/5/2026 11:23 | 4/5/2026 11:35 | 10 | 4/5/2026 11:42 | 4/5/2026 11:45 | 7 | 4/5/2026 11:55 | 4/5/2026 12:15 | 10 | 62 | 27
1 | SN379 | 4/5/2026 08:40 | 4/5/2026 08:50 | 4/5/2026 08:56 | 10 | 4/5/2026 09:03 | 4/5/2026 09:04 | 7 | 4/5/2026 09:14 | 4/5/2026 09:42 | 10 | 62 | 27
1 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:19 | 4/5/2026 06:21 | 1 | 4/5/2026 06:24 | 4/5/2026 06:26 | 3 | 10 | 4
1 | TB1552 | 4/5/2026 07:08 | 4/5/2026 07:18 | 4/5/2026 07:28 | 10 | 4/5/2026 07:35 | 4/5/2026 07:37 | 7 | 4/5/2026 07:47 | 4/5/2026 07:54 | 10 | 46 | 27
1 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:29 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 6 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 26
1 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:22 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 5 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 25
1 | TG934 | 4/5/2026 12:26 | 4/5/2026 12:26 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:14 | 0 | 48 | 0
1 | UA950 | 4/5/2026 08:45 | 4/5/2026 08:55 | 4/5/2026 09:09 | 10 | 4/5/2026 09:16 | 4/5/2026 09:17 | 7 | 4/5/2026 09:27 | 4/5/2026 09:53 | 10 | 68 | 27
1 | UA994 | 4/5/2026 11:37 | 4/5/2026 11:42 | 4/5/2026 11:56 | 5 | 4/5/2026 11:58 | 4/5/2026 12:01 | 2 | 4/5/2026 12:07 | 4/5/2026 12:37 | 6 | 60 | 13
1 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:14 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 5 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 25
2 | AC832 | 4/5/2026 11:38 | 4/5/2026 11:38 | 4/5/2026 11:48 | 0 | 4/5/2026 11:48 | 4/5/2026 11:50 | 0 | 4/5/2026 11:50 | 4/5/2026 12:13 | 0 | 35 | 0
2 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:13 | 0 | 4/5/2026 12:13 | 4/5/2026 12:14 | 0 | 4/5/2026 12:14 | 4/5/2026 13:00 | 0 | 86 | 0
2 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:48 | 4/5/2026 12:58 | 0 | 4/5/2026 12:58 | 4/5/2026 13:00 | 0 | 4/5/2026 13:00 | 4/5/2026 13:07 | 0 | 19 | 0
2 | LH1004 | 4/5/2026 09:53 | 4/5/2026 10:03 | 4/5/2026 10:05 | 10 | 4/5/2026 10:12 | 4/5/2026 10:14 | 7 | 4/5/2026 10:24 | 4/5/2026 10:31 | 10 | 38 | 27
2 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:25 | 4/5/2026 09:27 | 6 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 26
2 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:40 | 10 | 4/5/2026 07:44 | 4/5/2026 07:46 | 4 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 24
2 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 06:59 | 0 | 4/5/2026 06:59 | 4/5/2026 07:01 | 0 | 4/5/2026 07:07 | 4/5/2026 07:30 | 6 | 42 | 6
2 | SN229 | 4/5/2026 10:26 | 4/5/2026 10:26 | 4/5/2026 10:34 | 0 | 4/5/2026 10:34 | 4/5/2026 10:36 | 0 | 4/5/2026 10:37 | 4/5/2026 11:06 | 1 | 40 | 1
2 | SN278 | 4/5/2026 12:41 | 4/5/2026 12:41 | 4/5/2026 12:47 | 0 | 4/5/2026 12:47 | 4/5/2026 12:49 | 0 | 4/5/2026 12:49 | 4/5/2026 13:18 | 0 | 37 | 0
2 | SN2900 | 4/5/2026 08:33 | 4/5/2026 08:33 | 4/5/2026 08:40 | 0 | 4/5/2026 08:40 | 4/5/2026 08:42 | 0 | 4/5/2026 08:42 | 4/5/2026 08:46 | 0 | 13 | 0
2 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:49 | 0 | 4/5/2026 11:51 | 4/5/2026 11:52 | 2 | 4/5/2026 11:58 | 4/5/2026 12:04 | 6 | 23 | 8
2 | SN358 | 4/5/2026 08:24 | 4/5/2026 08:33 | 4/5/2026 08:46 | 9 | 4/5/2026 08:53 | 4/5/2026 08:54 | 7 | 4/5/2026 09:04 | 4/5/2026 09:31 | 10 | 67 | 26
2 | SN379 | 4/5/2026 11:03 | 4/5/2026 11:03 | 4/5/2026 11:19 | 0 | 4/5/2026 11:19 | 4/5/2026 11:21 | 0 | 4/5/2026 11:21 | 4/5/2026 11:58 | 0 | 55 | 0
2 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:18 | 4/5/2026 06:19 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 5 | 10 | 5
2 | TB1552 | 4/5/2026 07:08 | 4/5/2026 07:18 | 4/5/2026 07:29 | 10 | 4/5/2026 07:36 | 4/5/2026 07:38 | 7 | 4/5/2026 07:48 | 4/5/2026 07:55 | 10 | 47 | 27
2 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:30 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 5 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 25
2 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:21 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 6 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 26
2 | TG934 | 4/5/2026 09:16 | 4/5/2026 09:26 | 4/5/2026 09:43 | 10 | 4/5/2026 09:50 | 4/5/2026 09:52 | 7 | 4/5/2026 10:02 | 4/5/2026 10:22 | 10 | 66 | 27
2 | UA950 | 4/5/2026 09:58 | 4/5/2026 10:08 | 4/5/2026 10:30 | 10 | 4/5/2026 10:37 | 4/5/2026 10:40 | 7 | 4/5/2026 10:50 | 4/5/2026 11:17 | 10 | 79 | 27
2 | UA994 | 4/5/2026 11:28 | 4/5/2026 11:38 | 4/5/2026 11:47 | 10 | 4/5/2026 11:54 | 4/5/2026 11:57 | 7 | 4/5/2026 12:07 | 4/5/2026 12:32 | 10 | 64 | 27
2 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:12 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 7 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 27
3 | AC832 | 4/5/2026 07:46 | 4/5/2026 07:56 | 4/5/2026 08:07 | 10 | 4/5/2026 08:14 | 4/5/2026 08:16 | 7 | 4/5/2026 08:26 | 4/5/2026 08:53 | 10 | 67 | 27
3 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:14 | 0 | 4/5/2026 12:14 | 4/5/2026 12:16 | 0 | 4/5/2026 12:16 | 4/5/2026 13:02 | 0 | 88 | 0
3 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:48 | 4/5/2026 12:58 | 0 | 4/5/2026 12:58 | 4/5/2026 13:00 | 0 | 4/5/2026 13:00 | 4/5/2026 13:07 | 0 | 19 | 0
3 | LH1004 | 4/5/2026 08:53 | 4/5/2026 08:54 | 4/5/2026 08:56 | 1 | 4/5/2026 08:56 | 4/5/2026 08:57 | 0 | 4/5/2026 08:57 | 4/5/2026 09:03 | 0 | 10 | 1
3 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:17 | 4/5/2026 09:18 | 9 | 4/5/2026 09:25 | 4/5/2026 09:27 | 7 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 26
3 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:39 | 10 | 4/5/2026 07:44 | 4/5/2026 07:46 | 5 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 25
3 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:00 | 0 | 4/5/2026 07:03 | 4/5/2026 07:05 | 3 | 4/5/2026 07:07 | 4/5/2026 07:30 | 2 | 42 | 5
3 | SN229 | 4/5/2026 09:20 | 4/5/2026 09:29 | 4/5/2026 09:42 | 9 | 4/5/2026 09:49 | 4/5/2026 09:50 | 7 | 4/5/2026 10:00 | 4/5/2026 10:41 | 10 | 81 | 26
3 | SN278 | 4/5/2026 10:42 | 4/5/2026 10:47 | 4/5/2026 11:05 | 5 | 4/5/2026 11:12 | 4/5/2026 11:14 | 7 | 4/5/2026 11:24 | 4/5/2026 11:36 | 10 | 54 | 22
3 | SN2900 | 4/5/2026 07:25 | 4/5/2026 07:35 | 4/5/2026 07:41 | 10 | 4/5/2026 07:48 | 4/5/2026 07:51 | 7 | 4/5/2026 08:01 | 4/5/2026 08:16 | 10 | 51 | 27
3 | SN3326 | 4/5/2026 08:05 | 4/5/2026 08:15 | 4/5/2026 08:22 | 10 | 4/5/2026 08:29 | 4/5/2026 08:31 | 7 | 4/5/2026 08:41 | 4/5/2026 09:01 | 10 | 56 | 27
3 | SN358 | 4/5/2026 11:13 | 4/5/2026 11:23 | 4/5/2026 11:34 | 10 | 4/5/2026 11:41 | 4/5/2026 11:43 | 7 | 4/5/2026 11:53 | 4/5/2026 12:13 | 10 | 60 | 27
3 | SN379 | 4/5/2026 08:40 | 4/5/2026 08:50 | 4/5/2026 08:55 | 10 | 4/5/2026 09:02 | 4/5/2026 09:04 | 7 | 4/5/2026 09:14 | 4/5/2026 09:42 | 10 | 62 | 27
3 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:18 | 4/5/2026 06:20 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 4 | 10 | 4
3 | TB1552 | 4/5/2026 07:08 | 4/5/2026 07:18 | 4/5/2026 07:30 | 10 | 4/5/2026 07:37 | 4/5/2026 07:38 | 7 | 4/5/2026 07:48 | 4/5/2026 07:55 | 10 | 47 | 27
3 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:28 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 7 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 27
3 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:22 | 10 | 4/5/2026 09:29 | 4/5/2026 09:31 | 7 | 4/5/2026 09:38 | 4/5/2026 09:46 | 7 | 42 | 24
3 | TG934 | 4/5/2026 12:26 | 4/5/2026 12:26 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:14 | 0 | 48 | 0
3 | UA950 | 4/5/2026 08:20 | 4/5/2026 08:30 | 4/5/2026 08:43 | 10 | 4/5/2026 08:50 | 4/5/2026 08:53 | 7 | 4/5/2026 09:03 | 4/5/2026 09:52 | 10 | 92 | 27
3 | UA994 | 4/5/2026 10:01 | 4/5/2026 10:11 | 4/5/2026 10:22 | 10 | 4/5/2026 10:29 | 4/5/2026 10:31 | 7 | 4/5/2026 10:41 | 4/5/2026 11:05 | 10 | 64 | 27
3 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:12 | 10 | 4/5/2026 09:19 | 4/5/2026 09:20 | 7 | 4/5/2026 09:30 | 4/5/2026 09:33 | 10 | 37 | 27
4 | AC832 | 4/5/2026 07:46 | 4/5/2026 07:56 | 4/5/2026 08:05 | 10 | 4/5/2026 08:12 | 4/5/2026 08:14 | 7 | 4/5/2026 08:24 | 4/5/2026 08:51 | 10 | 65 | 27
4 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:06 | 0 | 4/5/2026 12:06 | 4/5/2026 12:08 | 0 | 4/5/2026 12:10 | 4/5/2026 12:56 | 2 | 82 | 2
4 | FH8116 | 4/5/2026 06:00 | 4/5/2026 06:10 | 4/5/2026 06:11 | 10 | 4/5/2026 06:18 | 4/5/2026 06:20 | 7 | 4/5/2026 06:30 | 4/5/2026 06:32 | 10 | 32 | 27
4 | LH1004 | 4/5/2026 08:53 | 4/5/2026 09:03 | 4/5/2026 09:05 | 10 | 4/5/2026 09:07 | 4/5/2026 09:09 | 2 | 4/5/2026 09:18 | 4/5/2026 09:24 | 9 | 31 | 21
4 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:24 | 4/5/2026 09:27 | 5 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 25
4 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:39 | 10 | 4/5/2026 07:44 | 4/5/2026 07:46 | 5 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 25
4 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:01 | 0 | 4/5/2026 07:01 | 4/5/2026 07:03 | 0 | 4/5/2026 07:07 | 4/5/2026 07:30 | 4 | 42 | 4
4 | SN229 | 4/5/2026 09:20 | 4/5/2026 09:30 | 4/5/2026 09:39 | 10 | 4/5/2026 09:46 | 4/5/2026 09:47 | 7 | 4/5/2026 09:57 | 4/5/2026 10:38 | 10 | 78 | 27
4 | SN278 | 4/5/2026 12:41 | 4/5/2026 12:41 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 12:47 | 0 | 4/5/2026 12:47 | 4/5/2026 13:16 | 0 | 35 | 0
4 | SN2900 | 4/5/2026 11:04 | 4/5/2026 11:04 | 4/5/2026 11:09 | 0 | 4/5/2026 11:09 | 4/5/2026 11:11 | 0 | 4/5/2026 11:11 | 4/5/2026 11:32 | 0 | 28 | 0
4 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:48 | 0 | 4/5/2026 11:48 | 4/5/2026 11:50 | 0 | 4/5/2026 11:50 | 4/5/2026 11:56 | 0 | 15 | 0
4 | SN358 | 4/5/2026 12:23 | 4/5/2026 12:23 | 4/5/2026 12:40 | 0 | 4/5/2026 12:45 | 4/5/2026 12:47 | 5 | 4/5/2026 12:56 | 4/5/2026 13:27 | 9 | 64 | 14
4 | SN379 | 4/5/2026 08:40 | 4/5/2026 08:50 | 4/5/2026 08:57 | 10 | 4/5/2026 09:04 | 4/5/2026 09:05 | 7 | 4/5/2026 09:15 | 4/5/2026 09:43 | 10 | 63 | 27
4 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:19 | 0 | 4/5/2026 06:22 | 4/5/2026 06:24 | 3 | 4/5/2026 06:24 | 4/5/2026 06:26 | 0 | 10 | 3
4 | TB1552 | 4/5/2026 10:31 | 4/5/2026 10:31 | 4/5/2026 10:44 | 0 | 4/5/2026 10:44 | 4/5/2026 10:46 | 0 | 4/5/2026 10:46 | 4/5/2026 10:55 | 0 | 24 | 0
4 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:32 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 3 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 23
4 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:21 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 6 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 26
4 | TG934 | 4/5/2026 09:16 | 4/5/2026 09:26 | 4/5/2026 09:44 | 10 | 4/5/2026 09:51 | 4/5/2026 09:53 | 7 | 4/5/2026 10:03 | 4/5/2026 10:23 | 10 | 67 | 27
4 | UA950 | 4/5/2026 08:45 | 4/5/2026 08:55 | 4/5/2026 09:06 | 10 | 4/5/2026 09:13 | 4/5/2026 09:14 | 7 | 4/5/2026 09:24 | 4/5/2026 09:50 | 10 | 65 | 27
4 | UA994 | 4/5/2026 10:01 | 4/5/2026 10:11 | 4/5/2026 10:23 | 10 | 4/5/2026 10:30 | 4/5/2026 10:32 | 7 | 4/5/2026 10:42 | 4/5/2026 11:06 | 10 | 65 | 27
4 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:13 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 6 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 26
5 | AC832 | 4/5/2026 10:43 | 4/5/2026 10:43 | 4/5/2026 10:56 | 0 | 4/5/2026 10:56 | 4/5/2026 10:58 | 0 | 4/5/2026 10:58 | 4/5/2026 11:32 | 0 | 49 | 0
5 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:04 | 0 | 4/5/2026 12:04 | 4/5/2026 12:06 | 0 | 4/5/2026 12:06 | 4/5/2026 12:52 | 0 | 78 | 0
5 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:48 | 4/5/2026 13:00 | 0 | 4/5/2026 13:03 | 4/5/2026 13:05 | 3 | 4/5/2026 13:15 | 4/5/2026 13:22 | 10 | 34 | 13
5 | LH1004 | 4/5/2026 12:50 | 4/5/2026 12:50 | 4/5/2026 12:55 | 0 | 4/5/2026 12:55 | 4/5/2026 12:57 | 0 | 4/5/2026 12:57 | 4/5/2026 13:24 | 0 | 34 | 0
5 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:24 | 4/5/2026 09:27 | 5 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 25
5 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:38 | 10 | 4/5/2026 07:45 | 4/5/2026 07:46 | 7 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 27
5 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:00 | 0 | 4/5/2026 07:00 | 4/5/2026 07:03 | 0 | 4/5/2026 07:07 | 4/5/2026 07:30 | 4 | 42 | 4
5 | SN229 | 4/5/2026 09:20 | 4/5/2026 09:30 | 4/5/2026 09:39 | 10 | 4/5/2026 09:46 | 4/5/2026 09:47 | 7 | 4/5/2026 09:57 | 4/5/2026 10:38 | 10 | 78 | 27
5 | SN278 | 4/5/2026 08:27 | 4/5/2026 08:28 | 4/5/2026 08:38 | 1 | 4/5/2026 08:45 | 4/5/2026 08:47 | 7 | 4/5/2026 08:57 | 4/5/2026 09:27 | 10 | 60 | 18
5 | SN2900 | 4/5/2026 07:25 | 4/5/2026 07:35 | 4/5/2026 07:40 | 10 | 4/5/2026 07:47 | 4/5/2026 07:49 | 7 | 4/5/2026 07:59 | 4/5/2026 08:14 | 10 | 49 | 27
5 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:49 | 0 | 4/5/2026 11:49 | 4/5/2026 11:50 | 0 | 4/5/2026 11:50 | 4/5/2026 11:56 | 0 | 15 | 0
5 | SN358 | 4/5/2026 12:23 | 4/5/2026 12:23 | 4/5/2026 12:36 | 0 | 4/5/2026 12:40 | 4/5/2026 12:42 | 4 | 4/5/2026 12:52 | 4/5/2026 13:23 | 10 | 60 | 14
5 | SN379 | 4/5/2026 08:40 | 4/5/2026 08:50 | 4/5/2026 08:55 | 10 | 4/5/2026 09:02 | 4/5/2026 09:04 | 7 | 4/5/2026 09:14 | 4/5/2026 09:42 | 10 | 62 | 27
5 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:18 | 4/5/2026 06:20 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 4 | 10 | 4
5 | TB1552 | 4/5/2026 07:43 | 4/5/2026 07:43 | 4/5/2026 07:48 | 0 | 4/5/2026 07:49 | 4/5/2026 07:51 | 1 | 4/5/2026 07:51 | 4/5/2026 07:55 | 0 | 12 | 1
5 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:18 | 4/5/2026 09:32 | 9 | 4/5/2026 09:37 | 4/5/2026 09:39 | 5 | 4/5/2026 09:47 | 4/5/2026 09:56 | 8 | 47 | 22
5 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:21 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 6 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 26
5 | TG934 | 4/5/2026 09:16 | 4/5/2026 09:26 | 4/5/2026 09:44 | 10 | 4/5/2026 09:51 | 4/5/2026 09:54 | 7 | 4/5/2026 10:04 | 4/5/2026 10:24 | 10 | 68 | 27
5 | UA950 | 4/5/2026 08:45 | 4/5/2026 08:55 | 4/5/2026 09:08 | 10 | 4/5/2026 09:15 | 4/5/2026 09:17 | 7 | 4/5/2026 09:27 | 4/5/2026 09:53 | 10 | 68 | 27
5 | UA994 | 4/5/2026 12:35 | 4/5/2026 12:35 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:15 | 0 | 40 | 0
5 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:05 | 4/5/2026 09:14 | 9 | 4/5/2026 09:20 | 4/5/2026 09:22 | 6 | 4/5/2026 09:31 | 4/5/2026 09:34 | 9 | 38 | 24
6 | AC832 | 4/5/2026 10:39 | 4/5/2026 10:39 | 4/5/2026 10:47 | 0 | 4/5/2026 10:47 | 4/5/2026 10:49 | 0 | 4/5/2026 10:59 | 4/5/2026 11:29 | 10 | 50 | 10
6 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:10 | 0 | 4/5/2026 12:10 | 4/5/2026 12:12 | 0 | 4/5/2026 12:12 | 4/5/2026 12:58 | 0 | 84 | 0
6 | FH8116 | 4/5/2026 06:00 | 4/5/2026 06:10 | 4/5/2026 06:12 | 10 | 4/5/2026 06:19 | 4/5/2026 06:20 | 7 | 4/5/2026 06:30 | 4/5/2026 06:32 | 10 | 32 | 27
6 | LH1004 | 4/5/2026 11:47 | 4/5/2026 11:47 | 4/5/2026 11:48 | 0 | 4/5/2026 11:48 | 4/5/2026 11:50 | 0 | 4/5/2026 11:50 | 4/5/2026 11:55 | 0 | 8 | 0
6 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:17 | 4/5/2026 09:18 | 9 | 4/5/2026 09:25 | 4/5/2026 09:27 | 7 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 26
6 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:38 | 10 | 4/5/2026 07:44 | 4/5/2026 07:46 | 6 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 26
6 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:53 | 4/5/2026 07:03 | 5 | 4/5/2026 07:04 | 4/5/2026 07:06 | 1 | 4/5/2026 07:07 | 4/5/2026 07:30 | 1 | 42 | 7
6 | SN229 | 4/5/2026 10:26 | 4/5/2026 10:26 | 4/5/2026 10:38 | 0 | 4/5/2026 10:38 | 4/5/2026 10:40 | 0 | 4/5/2026 10:40 | 4/5/2026 11:09 | 0 | 43 | 0
6 | SN278 | 4/5/2026 08:27 | 4/5/2026 08:37 | 4/5/2026 08:47 | 10 | 4/5/2026 08:54 | 4/5/2026 08:57 | 7 | 4/5/2026 09:07 | 4/5/2026 09:37 | 10 | 70 | 27
6 | SN2900 | 4/5/2026 11:04 | 4/5/2026 11:04 | 4/5/2026 11:08 | 0 | 4/5/2026 11:08 | 4/5/2026 11:10 | 0 | 4/5/2026 11:10 | 4/5/2026 11:31 | 0 | 27 | 0
6 | SN3326 | 4/5/2026 08:05 | 4/5/2026 08:15 | 4/5/2026 08:24 | 10 | 4/5/2026 08:31 | 4/5/2026 08:32 | 7 | 4/5/2026 08:42 | 4/5/2026 09:02 | 10 | 57 | 27
6 | SN358 | 4/5/2026 12:23 | 4/5/2026 12:33 | 4/5/2026 12:45 | 10 | 4/5/2026 12:50 | 4/5/2026 12:52 | 5 | 4/5/2026 12:58 | 4/5/2026 13:29 | 6 | 66 | 21
6 | SN379 | 4/5/2026 11:03 | 4/5/2026 11:03 | 4/5/2026 11:17 | 0 | 4/5/2026 11:17 | 4/5/2026 11:19 | 0 | 4/5/2026 11:19 | 4/5/2026 11:56 | 0 | 53 | 0
6 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:18 | 4/5/2026 06:20 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 4 | 10 | 4
6 | TB1552 | 4/5/2026 07:43 | 4/5/2026 07:43 | 4/5/2026 07:49 | 0 | 4/5/2026 07:49 | 4/5/2026 07:51 | 0 | 4/5/2026 07:51 | 4/5/2026 07:55 | 0 | 12 | 0
6 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:28 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 7 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 27
6 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:20 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 7 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 27
6 | TG934 | 4/5/2026 12:26 | 4/5/2026 12:26 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:14 | 0 | 48 | 0
6 | UA950 | 4/5/2026 11:58 | 4/5/2026 11:58 | 4/5/2026 12:09 | 0 | 4/5/2026 12:09 | 4/5/2026 12:11 | 0 | 4/5/2026 12:11 | 4/5/2026 12:39 | 0 | 41 | 0
6 | UA994 | 4/5/2026 08:32 | 4/5/2026 08:42 | 4/5/2026 08:57 | 10 | 4/5/2026 09:04 | 4/5/2026 09:06 | 7 | 4/5/2026 09:16 | 4/5/2026 09:49 | 10 | 77 | 27
6 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:14 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 5 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 25
7 | AC832 | 4/5/2026 07:46 | 4/5/2026 07:56 | 4/5/2026 08:06 | 10 | 4/5/2026 08:13 | 4/5/2026 08:15 | 7 | 4/5/2026 08:25 | 4/5/2026 08:52 | 10 | 66 | 27
7 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:11 | 0 | 4/5/2026 12:11 | 4/5/2026 12:13 | 0 | 4/5/2026 12:14 | 4/5/2026 13:00 | 1 | 86 | 1
7 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:49 | 4/5/2026 12:58 | 1 | 4/5/2026 13:05 | 4/5/2026 13:07 | 7 | 4/5/2026 13:14 | 4/5/2026 13:21 | 7 | 33 | 15
7 | LH1004 | 4/5/2026 11:47 | 4/5/2026 11:47 | 4/5/2026 11:49 | 0 | 4/5/2026 11:49 | 4/5/2026 11:51 | 0 | 4/5/2026 11:51 | 4/5/2026 11:56 | 0 | 9 | 0
7 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:17 | 4/5/2026 09:18 | 9 | 4/5/2026 09:25 | 4/5/2026 09:27 | 7 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 26
7 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:27 | 4/5/2026 07:38 | 8 | 4/5/2026 07:45 | 4/5/2026 07:46 | 7 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 25
7 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 06:57 | 0 | 4/5/2026 06:57 | 4/5/2026 07:00 | 0 | 4/5/2026 07:07 | 4/5/2026 07:30 | 7 | 42 | 7
7 | SN229 | 4/5/2026 10:26 | 4/5/2026 10:26 | 4/5/2026 10:36 | 0 | 4/5/2026 10:36 | 4/5/2026 10:38 | 0 | 4/5/2026 10:38 | 4/5/2026 11:07 | 0 | 41 | 0
7 | SN278 | 4/5/2026 12:41 | 4/5/2026 12:51 | 4/5/2026 12:56 | 10 | 4/5/2026 13:02 | 4/5/2026 13:04 | 6 | 4/5/2026 13:14 | 4/5/2026 13:43 | 10 | 62 | 26
7 | SN2900 | 4/5/2026 11:04 | 4/5/2026 11:04 | 4/5/2026 11:08 | 0 | 4/5/2026 11:08 | 4/5/2026 11:10 | 0 | 4/5/2026 11:10 | 4/5/2026 11:31 | 0 | 27 | 0
7 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:51 | 0 | 4/5/2026 11:51 | 4/5/2026 11:52 | 0 | 4/5/2026 11:54 | 4/5/2026 12:00 | 2 | 19 | 2
7 | SN358 | 4/5/2026 12:23 | 4/5/2026 12:32 | 4/5/2026 12:49 | 9 | 4/5/2026 12:50 | 4/5/2026 12:51 | 1 | 4/5/2026 13:00 | 4/5/2026 13:31 | 9 | 68 | 19
7 | SN379 | 4/5/2026 11:03 | 4/5/2026 11:03 | 4/5/2026 11:14 | 0 | 4/5/2026 11:14 | 4/5/2026 11:17 | 0 | 4/5/2026 11:17 | 4/5/2026 11:54 | 0 | 51 | 0
7 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:19 | 0 | 4/5/2026 06:20 | 4/5/2026 06:22 | 1 | 4/5/2026 06:24 | 4/5/2026 06:26 | 2 | 10 | 3
7 | TB1552 | 4/5/2026 08:25 | 4/5/2026 08:25 | 4/5/2026 08:44 | 0 | 4/5/2026 08:44 | 4/5/2026 08:46 | 0 | 4/5/2026 08:46 | 4/5/2026 08:54 | 0 | 29 | 0
7 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:09 | 4/5/2026 09:18 | 0 | 4/5/2026 09:18 | 4/5/2026 09:19 | 0 | 4/5/2026 09:22 | 4/5/2026 09:31 | 3 | 22 | 3
7 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:13 | 4/5/2026 09:20 | 9 | 4/5/2026 09:27 | 4/5/2026 09:29 | 7 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 26
7 | TG934 | 4/5/2026 12:26 | 4/5/2026 12:26 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:14 | 0 | 48 | 0
7 | UA950 | 4/5/2026 11:58 | 4/5/2026 11:58 | 4/5/2026 12:11 | 0 | 4/5/2026 12:11 | 4/5/2026 12:14 | 0 | 4/5/2026 12:14 | 4/5/2026 12:42 | 0 | 44 | 0
7 | UA994 | 4/5/2026 12:35 | 4/5/2026 12:35 | 4/5/2026 12:42 | 0 | 4/5/2026 12:42 | 4/5/2026 12:44 | 0 | 4/5/2026 12:44 | 4/5/2026 13:14 | 0 | 39 | 0
7 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:13 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 6 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 26
8 | AC832 | 4/5/2026 07:46 | 4/5/2026 07:56 | 4/5/2026 08:06 | 10 | 4/5/2026 08:13 | 4/5/2026 08:15 | 7 | 4/5/2026 08:25 | 4/5/2026 08:52 | 10 | 66 | 27
8 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:15 | 0 | 4/5/2026 12:15 | 4/5/2026 12:17 | 0 | 4/5/2026 12:17 | 4/5/2026 13:03 | 0 | 89 | 0
8 | FH8116 | 4/5/2026 06:00 | 4/5/2026 06:10 | 4/5/2026 06:12 | 10 | 4/5/2026 06:19 | 4/5/2026 06:21 | 7 | 4/5/2026 06:31 | 4/5/2026 06:33 | 10 | 33 | 27
8 | LH1004 | 4/5/2026 08:53 | 4/5/2026 09:03 | 4/5/2026 09:06 | 10 | 4/5/2026 09:13 | 4/5/2026 09:15 | 7 | 4/5/2026 09:25 | 4/5/2026 09:31 | 10 | 38 | 27
8 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:24 | 4/5/2026 09:27 | 5 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 25
8 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:40 | 10 | 4/5/2026 07:45 | 4/5/2026 07:46 | 5 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 25
8 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:00 | 0 | 4/5/2026 07:00 | 4/5/2026 07:03 | 0 | 4/5/2026 07:07 | 4/5/2026 07:30 | 4 | 42 | 4
8 | SN229 | 4/5/2026 10:26 | 4/5/2026 10:26 | 4/5/2026 10:37 | 0 | 4/5/2026 10:37 | 4/5/2026 10:39 | 0 | 4/5/2026 10:39 | 4/5/2026 11:08 | 0 | 42 | 0
8 | SN278 | 4/5/2026 12:41 | 4/5/2026 12:51 | 4/5/2026 12:55 | 10 | 4/5/2026 13:02 | 4/5/2026 13:04 | 7 | 4/5/2026 13:14 | 4/5/2026 13:43 | 10 | 62 | 27
8 | SN2900 | 4/5/2026 07:25 | 4/5/2026 07:35 | 4/5/2026 07:39 | 10 | 4/5/2026 07:46 | 4/5/2026 07:48 | 7 | 4/5/2026 07:58 | 4/5/2026 08:13 | 10 | 48 | 27
8 | SN3326 | 4/5/2026 08:05 | 4/5/2026 08:15 | 4/5/2026 08:24 | 10 | 4/5/2026 08:31 | 4/5/2026 08:33 | 7 | 4/5/2026 08:43 | 4/5/2026 09:03 | 10 | 58 | 27
8 | SN358 | 4/5/2026 08:24 | 4/5/2026 08:34 | 4/5/2026 08:44 | 10 | 4/5/2026 08:51 | 4/5/2026 08:52 | 7 | 4/5/2026 09:02 | 4/5/2026 09:29 | 10 | 65 | 27
8 | SN379 | 4/5/2026 11:03 | 4/5/2026 11:03 | 4/5/2026 11:16 | 0 | 4/5/2026 11:16 | 4/5/2026 11:18 | 0 | 4/5/2026 11:18 | 4/5/2026 11:55 | 0 | 52 | 0
8 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:19 | 0 | 4/5/2026 06:19 | 4/5/2026 06:21 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 3 | 10 | 3
8 | TB1552 | 4/5/2026 07:08 | 4/5/2026 07:18 | 4/5/2026 07:31 | 10 | 4/5/2026 07:38 | 4/5/2026 07:40 | 7 | 4/5/2026 07:50 | 4/5/2026 07:57 | 10 | 49 | 27
8 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:17 | 4/5/2026 09:27 | 8 | 4/5/2026 09:34 | 4/5/2026 09:37 | 7 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 25
8 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:12 | 4/5/2026 09:21 | 8 | 4/5/2026 09:27 | 4/5/2026 09:29 | 6 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 24
8 | TG934 | 4/5/2026 12:26 | 4/5/2026 12:26 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:14 | 0 | 48 | 0
8 | UA950 | 4/5/2026 11:58 | 4/5/2026 11:58 | 4/5/2026 12:07 | 0 | 4/5/2026 12:07 | 4/5/2026 12:11 | 0 | 4/5/2026 12:11 | 4/5/2026 12:39 | 0 | 41 | 0
8 | UA994 | 4/5/2026 11:37 | 4/5/2026 11:37 | 4/5/2026 11:50 | 0 | 4/5/2026 11:54 | 4/5/2026 11:57 | 4 | 4/5/2026 12:07 | 4/5/2026 12:37 | 10 | 60 | 14
8 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:12 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 7 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 27
9 | AC832 | 4/5/2026 11:38 | 4/5/2026 11:38 | 4/5/2026 11:47 | 0 | 4/5/2026 11:47 | 4/5/2026 11:49 | 0 | 4/5/2026 11:49 | 4/5/2026 12:12 | 0 | 34 | 0
9 | ET750 | 4/5/2026 09:13 | 4/5/2026 09:23 | 4/5/2026 09:49 | 10 | 4/5/2026 09:56 | 4/5/2026 09:58 | 7 | 4/5/2026 10:08 | 4/5/2026 11:12 | 10 | 119 | 27
9 | FH8116 | 4/5/2026 12:48 | 4/5/2026 12:48 | 4/5/2026 13:01 | 0 | 4/5/2026 13:03 | 4/5/2026 13:05 | 2 | 4/5/2026 13:15 | 4/5/2026 13:22 | 10 | 34 | 12
9 | LH1004 | 4/5/2026 11:47 | 4/5/2026 11:47 | 4/5/2026 11:49 | 0 | 4/5/2026 11:49 | 4/5/2026 11:51 | 0 | 4/5/2026 11:51 | 4/5/2026 11:56 | 0 | 9 | 0
9 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:18 | 4/5/2026 09:19 | 10 | 4/5/2026 09:24 | 4/5/2026 09:27 | 5 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 25
9 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:27 | 4/5/2026 07:37 | 8 | 4/5/2026 07:44 | 4/5/2026 07:46 | 7 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 25
9 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:02 | 0 | 4/5/2026 07:04 | 4/5/2026 07:06 | 2 | 4/5/2026 07:07 | 4/5/2026 07:30 | 1 | 42 | 3
9 | SN229 | 4/5/2026 12:12 | 4/5/2026 12:12 | 4/5/2026 12:14 | 0 | 4/5/2026 12:14 | 4/5/2026 12:16 | 0 | 4/5/2026 12:16 | 4/5/2026 12:40 | 0 | 28 | 0
9 | SN278 | 4/5/2026 08:27 | 4/5/2026 08:37 | 4/5/2026 08:46 | 10 | 4/5/2026 08:53 | 4/5/2026 08:56 | 7 | 4/5/2026 09:06 | 4/5/2026 09:36 | 10 | 69 | 27
9 | SN2900 | 4/5/2026 07:25 | 4/5/2026 07:35 | 4/5/2026 07:40 | 10 | 4/5/2026 07:47 | 4/5/2026 07:49 | 7 | 4/5/2026 07:59 | 4/5/2026 08:14 | 10 | 49 | 27
9 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:52 | 0 | 4/5/2026 11:52 | 4/5/2026 11:53 | 0 | 4/5/2026 11:53 | 4/5/2026 11:59 | 0 | 18 | 0
9 | SN358 | 4/5/2026 12:23 | 4/5/2026 12:23 | 4/5/2026 12:35 | 0 | 4/5/2026 12:35 | 4/5/2026 12:37 | 0 | 4/5/2026 12:37 | 4/5/2026 13:08 | 0 | 45 | 0
9 | SN379 | 4/5/2026 08:40 | 4/5/2026 08:50 | 4/5/2026 08:56 | 10 | 4/5/2026 09:03 | 4/5/2026 09:04 | 7 | 4/5/2026 09:14 | 4/5/2026 09:42 | 10 | 62 | 27
9 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:18 | 4/5/2026 06:20 | 0 | 4/5/2026 06:24 | 4/5/2026 06:26 | 4 | 10 | 4
9 | TB1552 | 4/5/2026 08:25 | 4/5/2026 08:25 | 4/5/2026 08:38 | 0 | 4/5/2026 08:38 | 4/5/2026 08:40 | 0 | 4/5/2026 08:40 | 4/5/2026 08:48 | 0 | 23 | 0
9 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:19 | 4/5/2026 09:29 | 10 | 4/5/2026 09:35 | 4/5/2026 09:37 | 6 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 26
9 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:23 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 4 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 24
9 | TG934 | 4/5/2026 09:16 | 4/5/2026 09:26 | 4/5/2026 09:45 | 10 | 4/5/2026 09:52 | 4/5/2026 09:54 | 7 | 4/5/2026 10:04 | 4/5/2026 10:24 | 10 | 68 | 27
9 | UA950 | 4/5/2026 11:02 | 4/5/2026 11:02 | 4/5/2026 11:19 | 0 | 4/5/2026 11:19 | 4/5/2026 11:21 | 0 | 4/5/2026 11:21 | 4/5/2026 11:44 | 0 | 42 | 0
9 | UA994 | 4/5/2026 12:35 | 4/5/2026 12:35 | 4/5/2026 12:43 | 0 | 4/5/2026 12:43 | 4/5/2026 12:45 | 0 | 4/5/2026 12:45 | 4/5/2026 13:15 | 0 | 40 | 0
9 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:13 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 6 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 26
10 | AC832 | 4/5/2026 10:43 | 4/5/2026 10:43 | 4/5/2026 10:55 | 0 | 4/5/2026 10:55 | 4/5/2026 10:56 | 0 | 4/5/2026 10:56 | 4/5/2026 11:30 | 0 | 47 | 0
10 | ET750 | 4/5/2026 11:34 | 4/5/2026 11:34 | 4/5/2026 12:06 | 0 | 4/5/2026 12:06 | 4/5/2026 12:08 | 0 | 4/5/2026 12:14 | 4/5/2026 13:00 | 6 | 86 | 6
10 | FH8116 | 4/5/2026 06:00 | 4/5/2026 06:10 | 4/5/2026 06:11 | 10 | 4/5/2026 06:18 | 4/5/2026 06:20 | 7 | 4/5/2026 06:30 | 4/5/2026 06:32 | 10 | 32 | 27
10 | LH1004 | 4/5/2026 12:50 | 4/5/2026 12:50 | 4/5/2026 12:53 | 0 | 4/5/2026 12:53 | 4/5/2026 12:55 | 0 | 4/5/2026 12:55 | 4/5/2026 13:22 | 0 | 32 | 0
10 | SN1122 | 4/5/2026 09:08 | 4/5/2026 09:16 | 4/5/2026 09:17 | 8 | 4/5/2026 09:24 | 4/5/2026 09:27 | 7 | 4/5/2026 09:37 | 4/5/2026 09:38 | 10 | 30 | 25
10 | SN1124 | 4/5/2026 07:19 | 4/5/2026 07:29 | 4/5/2026 07:38 | 10 | 4/5/2026 07:44 | 4/5/2026 07:46 | 6 | 4/5/2026 07:56 | 4/5/2026 08:12 | 10 | 53 | 26
10 | SN206 | 4/5/2026 06:48 | 4/5/2026 06:48 | 4/5/2026 07:02 | 0 | 4/5/2026 07:03 | 4/5/2026 07:05 | 1 | 4/5/2026 07:07 | 4/5/2026 07:30 | 2 | 42 | 3
10 | SN229 | 4/5/2026 09:20 | 4/5/2026 09:30 | 4/5/2026 09:44 | 10 | 4/5/2026 09:51 | 4/5/2026 09:52 | 7 | 4/5/2026 10:02 | 4/5/2026 10:43 | 10 | 83 | 27
10 | SN278 | 4/5/2026 10:42 | 4/5/2026 10:51 | 4/5/2026 11:05 | 9 | 4/5/2026 11:12 | 4/5/2026 11:14 | 7 | 4/5/2026 11:24 | 4/5/2026 11:36 | 10 | 54 | 26
10 | SN2900 | 4/5/2026 08:33 | 4/5/2026 08:33 | 4/5/2026 08:39 | 0 | 4/5/2026 08:39 | 4/5/2026 08:40 | 0 | 4/5/2026 08:42 | 4/5/2026 08:46 | 2 | 13 | 2
10 | SN3326 | 4/5/2026 11:41 | 4/5/2026 11:41 | 4/5/2026 11:49 | 0 | 4/5/2026 11:49 | 4/5/2026 11:51 | 0 | 4/5/2026 11:55 | 4/5/2026 12:01 | 4 | 20 | 4
10 | SN358 | 4/5/2026 11:13 | 4/5/2026 11:23 | 4/5/2026 11:33 | 10 | 4/5/2026 11:40 | 4/5/2026 11:42 | 7 | 4/5/2026 11:52 | 4/5/2026 12:12 | 10 | 59 | 27
10 | SN379 | 4/5/2026 11:03 | 4/5/2026 11:03 | 4/5/2026 11:16 | 0 | 4/5/2026 11:16 | 4/5/2026 11:18 | 0 | 4/5/2026 11:18 | 4/5/2026 11:55 | 0 | 52 | 0
10 | SN3800 | 4/5/2026 06:16 | 4/5/2026 06:16 | 4/5/2026 06:18 | 0 | 4/5/2026 06:22 | 4/5/2026 06:24 | 4 | 4/5/2026 06:24 | 4/5/2026 06:26 | 0 | 10 | 4
10 | TB1552 | 4/5/2026 07:43 | 4/5/2026 07:43 | 4/5/2026 07:49 | 0 | 4/5/2026 07:49 | 4/5/2026 07:51 | 0 | 4/5/2026 07:51 | 4/5/2026 07:55 | 0 | 12 | 0
10 | TB2632 | 4/5/2026 09:09 | 4/5/2026 09:17 | 4/5/2026 09:28 | 8 | 4/5/2026 09:35 | 4/5/2026 09:37 | 7 | 4/5/2026 09:47 | 4/5/2026 09:56 | 10 | 47 | 25
10 | TB2662 | 4/5/2026 09:04 | 4/5/2026 09:14 | 4/5/2026 09:21 | 10 | 4/5/2026 09:27 | 4/5/2026 09:29 | 6 | 4/5/2026 09:39 | 4/5/2026 09:47 | 10 | 43 | 26
10 | TG934 | 4/5/2026 09:16 | 4/5/2026 09:26 | 4/5/2026 09:46 | 10 | 4/5/2026 09:53 | 4/5/2026 09:55 | 7 | 4/5/2026 10:05 | 4/5/2026 10:25 | 10 | 69 | 27
10 | UA950 | 4/5/2026 11:58 | 4/5/2026 11:58 | 4/5/2026 12:08 | 0 | 4/5/2026 12:08 | 4/5/2026 12:10 | 0 | 4/5/2026 12:10 | 4/5/2026 12:38 | 0 | 40 | 0
10 | UA994 | 4/5/2026 12:35 | 4/5/2026 12:35 | 4/5/2026 12:46 | 0 | 4/5/2026 12:46 | 4/5/2026 12:49 | 0 | 4/5/2026 12:49 | 4/5/2026 13:19 | 0 | 44 | 0
10 | XR5402 | 4/5/2026 08:56 | 4/5/2026 09:06 | 4/5/2026 09:13 | 10 | 4/5/2026 09:19 | 4/5/2026 09:21 | 6 | 4/5/2026 09:31 | 4/5/2026 09:34 | 10 | 38 | 26